## Sheet1
Go-live planner for an Oxford Mosaic website (switching over an existing domain name from an old site to a new Mosaic site)
| Action | Status | By Time/Date | Who | Comment
| Conditional formatting key: | To Do |  |  | See oxfordmosaic.web.ox.ac.uk/go-live for more detail on these steps
In Progress
Done
In advance
| Submit the domain name for adding to the SSL Certificate | To Do | well ahead | Site Admin | This is done fortnightly.
| Add the domain name to the SSL Certificate | To Do |  | Mosaic | This change has no effect until the site is put live.
| Review site set-up, content, accessibility and broken links | To Do |  | Site Admin
| Send request to the domain manager to update DNS to point domain(s) to Mosaic platform at 10am on go-live day (normally devolved to ITSS) | To Do |  | ITSS | Schedule 1-2 weeks in advance. See oxfordmosaic.web.ox.ac.uk/domains Separate CNAME record for each domain required.
| Request domain manager (normally devolved to ITSS) to immediately reduce the TTL for the domain being moved to 10 minutes. Also request to change it back to 7 days/normal interval two days after go-live | To Do |  | ITSS (or Central Networks Team) | Must be actioned 7 days in advance. If the Central Networks Team manage your domain and you want to schedule a specific day and time, they need at least three working days' notice.
| Add domain names as Custom Domains in Site Settings | To Do |  | Site Admin | This will not take effect until the domain is pointed on go-live day.
| Set the Primary Domain in Site Settings | To Do |  | Site Admin | This will not take effect until the domain is pointed on go-live day.
| If using Google Analytics, verify site ownership of the site on the Google Search Console - www.google.com/webmasters/tools/home?hl=en https://oxfordmosaic.web.ox.ac.uk/documentation/verify-ownership-google-search-console | To Do |  | Site Admin/ITSS | Must use the HTML file upload method to verify your account - if done already with another method this will fail after go-live of the new site. This can be done in advance because the search is associated with the domain name, not the physical site (i.e. it can be done while the domain names points to an existing site and it will move across to the new one with the domain name switch.
| Set up Redirects/Page aliases | To Do |  | Site Admin/ITSS | See oxfordmosaic.web.ox.ac.uk/urlsredirects
| Test redirects against the platform domain | To Do |  | Site Admin
| Amend text of the 404 page in Site Settings | To Do |  | Site Admin | Include a way for web users to contact you after go-live.
| Uncheck the option ‘Restrict site viewing to Content Editors only?’ in Site Settings > Visibility | To Do |  | Site Admin
| Check how site will look on mobile devices using Responsive Preview | To Do |  | Site Admin | Preview the mobile version of your site ¦ Oxford Mosaic
| Perform final review of the site. Invite stakeholders to review and sign-off site, as required. | To Do |  | Site Admin
Large public-facing sites only:
| Send current site analytics to Mosaic team to send on to Acquia | To Do |  | Site Admin | Large public-facing sites with high volume only.
| Send traffic information on to Acquia in advance of Go-Live day | To Do |  | Mosaic | Large public-facing sites with high volume only.
Go-live day: DD Month YYYY |  |  |  |  | Better to avoid Fridays and Mosaic release days
| Content updates limited to essential changes only | To Do | All day | Content Editors
| Site visibility: unhide site from search engines | To Do | 9:55 | Site Admin
| Update DNS to point domain(s) to Mosaic platform | To Do | 10:00 | ITSS | See https://oxfordmosaic.web.ox.ac.uk/domains#collapse280896 for more information
| Test site appears at new domain(s) | To Do | 10:00 - 11:00 | Site Admin
| Inform Mosaic Support Team site is live | To Do | 10:05 | Site Admin | Use Ask a Question web form: https://oxfordmosaic.web.ox.ac.uk/contact#tab-2640116 Normal service should now apply.
| Add Google Analytics tracking ID into Site Settings | To Do | 10:05 + | Site Admin | This is also needed to maintain the site ownership verification with the Google Search Console.
| Test redirects are working on moved domain(s) | To Do | 10:30 - 12:00 | Site Admin
| Check broken links | To Do | 11:00 | Site Admin | e.g. using a tool like Screaming Frog, https://www.screamingfrog.co.uk/seo-spider/pricing/
| Ask Google to re-index the site | To Do | 14:00 | Site Admin/ITSS | See https://support.google.com/webmasters/answer/6065812?hl=en. Please note: reindexing is NOT immediate. Google say 'it typically takes several days' Needs to be done by the person whose Google Account is verified as owning the site and associated to the Google Analytics tracker. To request Google Search re-indexing, use https://www.google.com/webmasters/tools (login with Google account required; see also information on https://en.wikipedia.org/wiki/Google_Search_Console)
Post live
| Check Google analytics is tracking new pages successfully | To Do | 2-3 days after launch | Site Admin
| Reinstate usual TTL interval (normally devolved to ITSS) | To Do | 2 days after launch | ITSS
| Check Google search is picking up new site's pages | To Do | 3-5 days after launch | Site Admin | It is likely to be several days before this appears
| Submit /sitemap.xml to Google Search Console | To Do | 3-5 days after launch | Site Admin/ITSS | This is optional, but is a good idea for a larger site, especially if the reindex didn't cover everything
| One week after go-live, run the Missing pages report to see URLs that have been requested which resulted in a 404 page not found message being delivered to the user. | To Do | 3-5 days after launch | Site Admin | May wish to add more redirects, aliases or pages
Notes
Contact details:
Site Admin:
ITSS:
Mosaic team: https://oxfordmosaic.web.ox.ac.uk/contact#tab-2600956

## Sheet2
To Do
In Progress
DONE